## Sayfa1
| Project Name | Project Duration | Start Date | End Date
| When The Ring Bells | 84 | 2019-10-01 | 2019-12-23
# | Task Name | Duration(Days) | Start Date | End Date | Resource Names | time axis 2019-10-01 to 2019-12-23
1 | Analyze Requerinment | 14 | 2019-10-01 | 2019-10-15 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-10-01 to 2019-10-15
2 | Project Planning | 5 | 2019-10-15 | 2019-10-20 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-10-15 to 2019-10-20
3 | Scenerio Writing | 10 | 2019-10-20 | 2019-10-30 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-10-20 to 2019-10-30
4 | Prepare RAD | 21 | 2019-10-15 | 2019-11-05 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-10-15 to 2019-11-05
5 | Redesign Existing Components | 11 | 2019-10-20 | 2019-10-31 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-10-20 to 2019-10-31
6 | Use Case Diagrams | 3 | 2019-11-01 | 2019-11-04 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-11-01 to 2019-11-04
7 | Sequence Diagram | 4 | 2019-11-01 | 2019-11-05 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-11-01 to 2019-11-05
8 | Class Diagram | 3 | 2019-11-06 | 2019-11-09 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-11-06 to 2019-11-09
9 | Sytem Requerinment Control | 5 | 2019-11-06 | 2019-11-11 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-11-06 to 2019-11-11
10 | Object Design Document | 21 | 2019-11-12 | 2019-12-03 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-11-12 to 2019-12-03
11 | System Design Document | 14 | 2019-12-03 | 2019-12-17 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-12-03 to 2019-12-17
12 | Fix | 5 | 2019-12-17 | 2019-12-22 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-12-17 to 2019-12-22
13 | Implementation | 35 | 2019-11-06 | 2019-12-11 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-11-06 to 2019-12-11
14 | Development | 28 | 2019-11-06 | 2019-12-04 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-11-06 to 2019-12-04
15 | Alpha/Quality Test | 9 | 2019-12-05 | 2019-12-14 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-12-05 to 2019-12-14
16 | Beta Test | 5 | 2019-12-15 | 2019-12-20 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-12-15 to 2019-12-20
17 | Release | 2 | 2019-12-21 | 2019-12-23 | Ersin, Serdar, Çağatay, Zafer | bar: 2019-12-21 to 2019-12-23
Formulas:
Start Date = [End Date, row above]
Start Date = [End Date, row above]+1
End Date = [Start Date]+[Project Duration]